Week 1
Week 2
Week 3
Week 4
Week 5
Dec 1
Feature
Tracking
Spike
Software
Architecture
1 & 2
Hardware Device 1
Feature
Set
Prototype 1
Plan Evaluation 1
Feature
Set
Feature
Set
Prototype 2
Hardware
Device 2
HW
Buy
(camera, touch)
Paper
Structure
Write
Related
Work
Plan
Evaluation
Plan
Evaluation 2

---
Week 6
Week 7
Week 8
Week 9
Week 10
Dec 22
Jan 12
Jan 19
Prepare Evalu
Run Pilot
Implementation Features Prototype 1
Implementation Features Prototype 2
Implementation
Feature Tracking
HW tricks
(flipping + stacking)
SW Implementation of HW tricks

---
Week 11
Week 12
Week 13
Week 14
Week 15
 Feb 2
Feb 9
Feb 16
Feb 23
Jan 26
Prototype 1 - evaluation
Results Writeup
Prepare Evaluation
Run Pilots
Refactoring

---
Week 16
Week 17
 Mar 9
Mar 2
Write up